## General
i.Logistic Transport Management System
COMPANY NAME |  | i.Logistic Pte Ltd |  |  |  | TODAY | 2021-11-05
PROJECT OWNER |  | Joleen Ng
PROJECT START |  | 2021-09-06
DISPLAY WEEK |  | 1
[6 empty] | 2021-09-06 | [6 empty] | 2021-09-13 | [6 empty] | 2021-09-20 | [6 empty] | 2021-09-27 | [6 empty] | 2021-10-04 | [6 empty] | 2021-10-11 | [6 empty] | 2021-10-18 | [6 empty] | 2021-10-25
 | time axis 2021-09-06 to 2021-10-31
S/N | TASK | PROGRESS | START | END | DAYS | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
1 | PROJECT HANDOVER
1.1 | Reading of Exisiting System Information | 100% | 2021-09-06 | 2021-09-10 | 5
1.2 | Reading of Current System Information | 100% | 2021-09-06 | 2021-09-10 | 5
1.3 | Exisiting System Familarization | 100% | 2021-09-06 | 2021-09-10 | 5
1.4 | Current System Familarization | 100% | 2021-09-06 | 2021-09-10 | 5
1.5 | Code Familarization | 100% | 2021-09-06 | 2021-09-10 | 5
2 | PROBLEM DEFINITION
2.1 | User Stories | 100% | 2021-09-13 | 2021-09-24 | 12
2.2 | Requirement Lisy | 100% | 2021-09-27 | 2021-10-01 | 5
2.3 | Product Backlog | 100% | 2021-09-27 | 2021-10-01 | 5
2.4 | Use-Case Diagram | 100% | 2021-09-27 | 2021-10-01 | 5
3 | PROJECT DESIGN
3.1 | Figma Design Prototype | 100% | 2021-10-04 | 2021-10-15 | 12
3.2 | Figma Design Prototype Refinement - Drivers | 100% | 2021-10-18 | 2021-10-22 | 5
3.3 | Figma Design Prototype Refinement - Coordinator | 50%
3.4 | Figma Design Prototype Refinement - Admin | 50%
3.5 | Figma Design Prototype Refinement - Customer | 50%
4 | PROJECT DEVELOPMENT
4.1 | Driver
4.1.1 | Front End Development | 0%
4.1.2 | Back End Development | 0%
4.2 | Coordinator
4.2.1 | Front End Development | 0%
4.2.2 | Back End Development | 0%
4.3 | Admin
4.3.1 | Front End Development | 0%
4.3.2 | Back End Development | 0%
4.4 | Admin
4.4.1 | Front End Development | 0%
4.4.2 | Back End Development | 0%
5 | Phase 5 Title
1.1 | Task 1
1.2 | Task 2
1.3 | Task 3
1.4 | Task 4
1.5 | Task 5
Formulas:
TODAY = [TODAY, row below]

## Sheet1
GANTT CHART
PROJECT TITLE |  | i.Logistics Transport Management System
PROJECT OWNER |  | Joleen Ng
S/N | TASK TITLE | START DATE (DD/MM/YYYY) | END DATE (DD/MM/YYYY) | DURATION (DAYS) | SEPTEMBER | [18 empty] | OCTOBER | [20 empty] | NOVEMBER | [21 empty] | DECEMBER
[5 empty] | WEEK 01 |  |  |  |  | WEEK 02 |  |  |  |  | WEEK 03 |  |  |  |  | WEEK 04 |  |  |  |  | WEEK 05 |  |  |  |  | WEEK 06 |  |  |  |  | WEEK 07 |  |  |  |  | WEEK 08 |  |  |  |  | WEEK 09 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 16 |  |  |  |  | WEEK 17
[5 empty] | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
1 | PROJECT HANDOVER
1.1 | Reading of Exisiting System Information | 2021-06-09 | 2021-10-09 | 5 days | bar: WEEK 01 M to WEEK 01 F
1.2 | Reading of Current System Information | 2021-06-09 | 2021-10-09 | 5 days | bar: WEEK 01 M to WEEK 01 F
1.3 | Exisiting System Familarization | 2021-06-09 | 2021-10-09 | 5 days | bar: WEEK 01 M to WEEK 01 F
1.4 | Current System Familarization | 2021-06-09 | 2021-10-09 | 5 days | bar: WEEK 01 M to WEEK 01 F
1.5 | Database Familarization | 2021-06-09 | 2021-09-24 | 15 days | bar: WEEK 01 M to WEEK 03 F
1.5 | Code Familarization | 2021-06-09 | 2021-09-24 | 15 days | bar: WEEK 01 M to WEEK 03 F
2 | PROJECT DEFINITION
2.1 | User Stories | 2021-09-13 | 2021-09-24 | 10 days | bar: WEEK 01 M to WEEK 03 F
2.2 | Requirement List | 2021-09-27 | 2021-01-10 | 5 days | bar: WEEK 01 M to WEEK 01 F; WEEK 04 M to WEEK 04 F
2.3 | Product Backlog | 2021-09-27 | 2021-01-10 | 5 days | bar: WEEK 01 M to WEEK 01 F; WEEK 04 M to WEEK 04 F
2.4 | Use-Case Diagram | 2021-09-27 | 2021-01-10 | 5 days | bar: WEEK 01 M to WEEK 01 F; WEEK 04 M to WEEK 04 F
3 | PROJECT DESIGN
3.1 | Figma Design Prototype - Webpage | 2021-04-10 | 2021-10-15 | 10 days | bar: WEEK 01 M to WEEK 01 F; WEEK 05 M to WEEK 06 F
3.2 | Figma Design Prototype - Mobile | 2021-04-10 | 2021-10-15 | 10 days | bar: WEEK 01 M to WEEK 01 F; WEEK 05 M to WEEK 06 F
3.3 | UI Flow Chart | 2021-04-10 | 2021-10-15 | 10 days | bar: WEEK 01 M to WEEK 01 F; WEEK 05 M to WEEK 06 F
3.4 | Figma Design Prototype Refinement - Drivers | 2021-10-18 | 2021-10-22 | 5 days | bar: WEEK 01 M to WEEK 01 F; WEEK 07 M to WEEK 07 F
4 | PROJECT DEVELOPMENT - MOBILE INTERFACE & WEB APPLICATION (FRONT-END/ BACK-END)
4.1 | Drivers Account - Front End (Web) | 2021-10-25 | 2021-02-11 | 7 days | bar: WEEK 01 M to WEEK 01 F; WEEK 08 M to WEEK 09 T
4.2 | Drivers Account - Front End (Mobile) | 2021-10-25 | 2021-05-11 | 10 days | bar: WEEK 01 M to WEEK 01 F; WEEK 08 M to WEEK 09 F
4.3 | Figma Design Prototype Refinement Flow - Admin. Coordinator, Customer | 2021-03-11 | 2021-12-11 | 7 days | bar: WEEK 01 M to WEEK 01 F; WEEK 09 W; WEEK 09 F to WEEK 10 F
4.4 | Setting up CI/CD environment for Web application | 2021-11-15 | 2021-11-15 | 1 day | bar: WEEK 01 M to WEEK 01 F; WEEK 11 M
4.5 | Admin Coordinator, Customer, SubCustomer Figma (Mobile) | 2021-11-15 | 2021-11-18 | 5 days | bar: WEEK 01 M to WEEK 01 F; WEEK 11 M to WEEK 11 F
4.6 | Admin - View Pending & Completed Jobs (Web) | 2021-11-16 | 2021-11-17 | 2 days | bar: WEEK 01 M to WEEK 01 F; WEEK 11 T to WEEK 11 W
4.7 | Admin - Assign Jobs (Web) | 2021-11-18 | 2021-11-19 | 2 days | bar: WEEK 01 M to WEEK 01 F; WEEK 11 T to WEEK 11 F

## Sheet2
GANTT CHART
S/N | TASK | START DATE (DD/MM/YYYY) | END DATE (DD/MM/YYYY) | DURATION (DAYS) | 2021-09-01 | [18 empty] | 2021-10-01 | [20 empty] | 2021-11-02 | [21 empty] | 2021-12-03 | [22 empty] | 2022-01-04 | [20 empty] | 2022-02-01 | [19 empty] | 2022-03-01 | [22 empty] | 2022-04-01
[5 empty] | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
[5 empty] | 6 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 1 | 4 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 15 | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 28 | 29 | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 29 | 1 | 2 | 3 | 6 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 31 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 25 | 28 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 25 | 28 | 29 | 30 | 31 | 1 | 4 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 15 | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 28 | 29
SPRINT 1: PROJECT HANDOVER | bar: 2022-04-01 F 1 to 2022-04-01 F 29
1.1 | Reading of Exisiting System Information | 2021-09-06 | 2021-09-10 | 5
1.2 | Reading of Current System Information | 2021-09-13 | 2021-09-17 | 5
1.3 | Exisiting System Familarization | 2021-09-06 | 2021-09-17 | 10
1.4 | Current System Familarization | 2021-10-20 | 2021-10-01 | 10
1.5 | Database Familarization | 2021-09-06 | 2021-10-01 | 20
1.6 | Code Familarization | 2021-09-06 | 2021-10-01 | 20
SPRINT 2: PROJECT REQUIREMENT | bar: 2022-04-01 F 1 to 2022-04-01 F 29
2.1 | User Stories | 2021-10-04 | 2021-10-06 | 3
2.2 | Use-Case Diagram | 2021-10-06 | 2021-10-08 | 3
2.3 | Product Backlog | 2021-10-11 | 2021-10-15 | 5
2.4 | Requirement List | 2021-10-11 | 2021-10-15 | 5
2.5 | User Interface Flow Chart | 2021-10-11 | 2021-10-15 | 5
SPRINT 3: PROJECT PROTOTPYE (FIGMA) | bar: 2022-04-01 F 1 to 2022-04-01 F 29
3.1 | Lo-Fi Prototype | 2021-10-18 | 2021-10-22 | 5
3.2 | Hi-Fi Prototype | 2021-10-25 | 2021-10-29 | 5
SPRINT 4 - 7: SOFTWARE DEVELOPMENT | bar: 2022-04-01 F 1 to 2022-04-01 F 29
4.1 | Mobile Application Front-End | 2021-11-01 | 2022-02-18 | 20
4.2 | Mobile Application Back-End | 2021-11-01 | 2022-02-18 | 20
SPRINT 8: INTEGRATION | bar: 2022-04-01 F 1 to 2022-04-01 F 29
8.1 | Mobile Application Front-End & Back-End Integration | 2021-02-21 | 2021-03-18 | 20
SPRINT 9: TESTING | bar: 2022-04-01 F 1 to 2022-04-01 F 29
9.1 | Test Cases Scenerio | 2021-03-07 | 2021-04-01 | 20
9.2 | Feedback with Drivers | 2021-03-21 | 2021-04-15 | 20
SPRINT 10: REPORT WRITING | bar: 2022-04-01 F 1 to 2022-04-01 F 29
10.1 | Capstone Final Trimester Writing | 2021-04-18 | 2021-04-29 | 10